## Sheet1
Risk management table
№ | Risk (cause-risk-effect) | Impact (1:4) | Likelihood (1:4) | Exposure | Mitigation | Overcoming risks
1 | Long-term procedure for approval of the project design by the customer - We will not be able to proceed to the next stage on time- The start of development will be delayed by the approval period. | 2 | 1 | 2 | Coordination with the customer and fixation of the maximum permissible number of days for approval of the layout. | Extension of the project for the duration of the design approval delay
2 | Начало боевых действий в районе физического размещения серверов - Частичное или полное повреждение серверов - полная или частичная блокировка разработки проекта. | 4 | 3 | 12 | Transferring servers to cloud storage. Monitoring the implementation of backups. | Negotiate and fix deadlines for restoring backup copies and complete it on time.
3 | The outbreak of hostilities in the area where servers are physically located - Partial or complete damage to servers - complete or partial blocking of project development. | 2 | 2 | 4 | Even distribution of tasks among team members, informing team members about the development process through regular meetings, motivating employees. | Negotiate and fix additional deadlines for attracting and implementing a new team member or training an existing one.
4 | Long-term illness, death, departure of a team member from the project - Unplanned absence of a team member - Lack of knowledge about the project, delay in project completion | 3 | 3 | 9 | Conducting an analysis of the proposed changes in order to identify how the change will affect the current state of the project, how much effort, money and time it will require for implementation. Timely provision of information to the customer about the possibility/impossibility and feasibility of making changes | Negotiate and fix additional deadlines and/or budget increases in case of significant changes in requirements.
5 | Late delivery of equipment for the project by third-party contractors or its inadequate quality - Absence or failure of equipment - Complete or partial blocking of a specific development stage, increase in project deadlines. | 2 | 2 | 4 | Choose a reliable equipment supplier. Conclude a warranty agreement with the supplier and possibly enter into a contract with the insurance company. | Order an immediate replacement of the equipment from the supplier and contact the insurance company for compensation.
6 | Long-term coordination of requirements by the customer and incorrect planning of deadlines - Release of a product by a competitor before ours - Loss of finances by the customer | 3 | 2 | 6 | Correct planning of project deadlines, establishing communication both within the team and within the project as a whole for quick acceptance, coordination and approval of requirements, details and stages of the project. Preliminary market analysis of competitors and tracking their activities. | Analysis of a competitor's released product in order to improve and expand the functionality of its own product to increase its competitiveness.
7 | Financial difficulties for the customer during the implementation of the project - Lack or decrease in project funding - Low productivity, decreased involvement of team members in the project | 4 | 2 | 8 | Stage-by-stage payment for the project, coordination of payment terms, tracking timely payment of the completed stage, coordination of the procedure in case of violation of payment terms. | Revision of requirements and/or reduction of work scope.
Risk explosure diagram
[7 empty] | Impact | 4 | 4 | 8 | 12 | 16 | Low
[8 empty] | 3 | 3 | 6 | 9 | 12 | Medium
[8 empty] | 2 | 2 | 4 | 6 | 8 | High
[8 empty] | 1 | 1 | 2 | 3 | 4 | Critical
[9 empty] | 1 | 2 | 3 | 4
Likelihood